Media Outreach Plan
East Region IPPE Committee

Draft 1

GOAL1: Establish relationship with local media in each city and town throughout East Region.
OBJECTIVE: Send quarterly press releases to every community newspaper in the rural counties and small towns in Spokane County. Establish primary contact for news media.
STRATEGIES:

1. By April, 2010 Gather contact information for community newspapers in all nine counties, using existing EREMS partnerships to identify community newspapers.
2. By April, 2010 create a letterhead for press releases with all IPPE Committee partner agencies listed.
3.  By May 2010 decide on primary media contact for EREMS IPPE.
4. By May 2010 identify topics for 2010 press releases.
5. Annually in May send press release during EMS week. Identify top injury areas for region, specify top injuries for specific county, provide suggestions on how to reduce individual injuries.
6. Annually in January and May identify topics for quarterly press releases. 

7. Annually, EREMS IPPE committee will record on a log the number of newspaper articles.
GOAL 2: Share Injury Prevention messages through media sources other than newspaper.
OBJECTIVE: Utilize social media and other avenues to share IPPE messages.

STRATEGIES:

1. By May 2010 encourage IPPE committee members to add the WA state Injury Prevention tag line and the CDC tagline to their email signature and/or agency website and print materials.
2. By May 2010 EREMS will post the WA State Injury Prevention message and the CDC tagline to their website.

3. By September 2010 EREMS will have links to each IPPE committee member agency website and will request each committee member agency links to EREMS.
4. By September 2010 EREMS IPPE Committee will identify which committee member agency has a facebook page or other social media outlet and request that they be linked to the EREMS website.

5. By September 2010 EREMS IPPE Committee will identify Spokane County partners with existing media contacts, such as Child Passenger Safety Team.

6. Annually, EREMS IPPE committee will record on a log the number of media contacts outside of press releases.

Ideas for 2010: 

EMS week - may
Fireworks – end june

Falls  -september

TBI/Sports – august 

Fall/Winter TBA

Create log: include falls help desk, Theresa CPS (ask Marion for details)
